## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Notes | Date started (actual date) | Date finished (actual date)
E01a | Add new customer | As a Bank Employee, I want to obtain a customer’s name, address and date of birth and the verify the details provided. Once verified, I can enter the detail to the system. So that I can add new customer to the system and request credit check. | 1 | 1 | • Verify that the customer does not exist in system • Make sure the customer credit status is recorded as unknown |  | 2018.4.10 | 2018.4.11
E01b | Confirm credit status | As a Bank Employee, I want update customer credit status as satisfactory once I receive the conformation from credit agency following a credit check. So that I can carry on to opening the account. | 1 | 1 | • Verify that customer exist in system matching details give. |  | 2018.4.12 | 2018.4.13
E01c | Create account | As a Bank Employee, I want to create an account of the type chosen for an existing customer, generate a unique account number and PIN. So that I can open the account and notify customer of account number and PIN. | 1 | 1 | • Verify that customer exists in system matching details given • Make sure that customer’s credit status has been recorded as satisfactory • Verify that account of required type is created • Verify that account number is unique • Verify that PIN is 4 digits. |  | 2018.4.14 | 2018.4.15
E02a | Deposit cash | As a Depositor I want to supply the account number and the amount of cash to be deposited So that I can deposit funds to the account in cash. | 1 | 2 | • Verify that account exists matching account number • Verify that the account is not inactive or suspended, otherwise return funds to depositor • Make sure that a receipt is issued to depositor • Make sure that deposit is marked as cleared • Make sure that balance of the account has changed because the depositor deposit fund in cash |  | 2018.4.20 | 2018.4.25
E02b | Deposit cheque | As a Depositor I want to supply the account number and the amount of cheque to be deposited So that I can deposit funds to the account in cheque. | 1 | 2 | • Verify that account exists matching account number • Verify that the account is not inactive or suspended, otherwise return funds to depositor • Make sure that deposit is marked as uncleared • Make sure that account records the number of funds deposited in cheque |  | 2018.4.26 | 2018.4.30
E02c | Withdraw | As a Withdrawer I want to supply the account number, PIN and the amount of money to be withdrawn So that I can withdraw funds from the account. | 1 | 2 | • Verify that account exists matching account number • Verify that the account is not inactive or suspended, otherwise return funds to withdrawer • Make sure that notice first if account is a saver account • Make sure that overdraft can be allowed only account is a current account. |  | 2018.5.1 | 2018.5.3
E03a | Give a notice | As a Bank Employee I want to be informed in advance about a withdrawal from a Saver account So that I can receive the notice before any withdrawal can be made from saver account | 2 | 3 | • Verify the type of the account is the saver account • A minimum period (e.g. in 7 days) must be given before any withdrawal can be made |  | 2018.5.9 | 2018.5.12
E03b | Check account | As a Bank Employee, I want to check the type of account and the balance of account So that I can know that how many funds I have and how many accounts I have. | 3 | 3 | • Verify the type and the number of accounts • Verify the balance of the costomer's accounts |  | 2018.5.13 | 2018.5.14
E03c | Check limit | As a Bank Employee, I want to check the overdraft limit of the account So that I can decide whether a customer may withdraw additional funds. | 3 | 3 | • Verify the type of the account is the current account • Verify that the amount of withdraw additional funds is not exceeding overdraft limit |  | 2018.5.15 | 2018.5.16
E04 | Clear funds | As a Clearing System, I want to clear the funds which used cheque to deposit So that I can clear un-cleared funds of the account periodically. | 1 | 4 | • Verity the fund deposited in cheque is marked as un-cleared at first • Make sure that the balance of account is changed because Clearing System clears un-cleared funds periodically. |  | 2018.5.17 | 2018.5.20
E05a | Suspend Account | As a Bank Employee I want to stop the transactions of the account in some situations So that the account can be suspended until the account is reinstated. | 4 | 5 | • Any type of the account can be suspended • If an account was suspended, no further transactions may occur until the account is reinstated |  | 2018.5.21 | 2018.5.22
E05b | Reinstate Account | As a Bank Employee I want to restore the transactions of the account in some situations So that the account can be reinstated when the account is suspended. | 4 | 5 | • Any type of the account can be reinstated • If an account was reinstated, all transactions will be restored |  | 2018.5.23 | 2018.5.24
E05c | Close Account | As a Customer, I want to stop my account service. So that I can choose to close my account. | 4 | 5 | • If the balance of the customer's account has been cleared, he/she can choose to close his/her account. |  | 2018.5.25 | 2018.5.26